## Inspection Log
Inspection_ID | Date | Site | Inspector | PM2.5_ugm3 | NOx_mgm3 | PM25_Status | NOx_Status | Evidence_Attached
INS-2024-001 | 03/01/2024 | Stevenage UK | M. Brown | 16 | 245.7 | Compliant | EXCEEDANCE | Yes
INS-2024-002 | 26/02/2024 | Ware UK | P. Davis | 17.4 | 141.8 | Compliant | Compliant | Yes
INS-2024-003 | 24/03/2024 | Worthing UK | S. Clark | 17.4 | 97.6 | Compliant | Compliant | Yes
INS-2024-004 | 23/04/2024 | Stevenage UK | J. Adams | 9.8 | 88 | Compliant | Compliant | Yes
INS-2024-005 | 22/05/2024 | Ware UK | M. Brown | 30.9 | 196.6 | EXCEEDANCE | Compliant | Yes
INS-2024-006 | 11/06/2024 | Montrose UK | P. Davis | 21.9 | 179.3 | Compliant | Compliant | Yes
INS-2024-007 | 13/07/2024 | Ware UK | M. Brown | 33.9 | 121.7 | EXCEEDANCE | Compliant | Yes
INS-2024-008 | 01/08/2024 | Montrose UK | M. Brown | 25.3 | 157.8 | EXCEEDANCE | Compliant | Yes
INS-2024-009 | 01/09/2024 | Ware UK | M. Brown | 20.1 | 157.3 | Compliant | Compliant | Yes
INS-2024-010 | 26/10/2024 | Stevenage UK | J. Adams | 15.5 | 206.7 | Compliant | EXCEEDANCE | Yes
INS-2024-011 | 12/11/2024 | Barnard Castle UK | M. Brown | 29.6 | 176.6 | EXCEEDANCE | Compliant | Yes
INS-2024-012 | 28/12/2024 | Worthing UK | S. Clark | 20.4 | 127.2 | Compliant | Compliant | Yes
INS-2024-013 | 19/01/2024 | Stevenage UK | S. Clark | 24.1 | 190 | Compliant | Compliant | Yes
INS-2024-014 | 06/02/2024 | Barnard Castle UK | J. Adams | 17.5 | 162.4 | Compliant | Compliant | Yes
INS-2024-015 | 08/03/2024 | Barnard Castle UK | J. Adams | 26.1 | 136.4 | EXCEEDANCE | Compliant | Yes
INS-2024-016 | 17/04/2024 | Worthing UK | P. Davis | 12.9 | 204.8 | Compliant | EXCEEDANCE | Yes
INS-2024-017 | 14/05/2024 | Ware UK | P. Davis | 24.1 | 183.5 | Compliant | Compliant | Yes
INS-2024-018 | 21/06/2024 | Ware UK | M. Brown | 25.2 | 204.8 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-019 | 11/07/2024 | Worthing UK | J. Adams | 21.2 | 105.3 | Compliant | Compliant | Yes
INS-2024-020 | 16/08/2024 | Ware UK | M. Brown | 31.4 | 251.3 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-021 | 17/09/2024 | Worthing UK | P. Davis | 30 | 253.5 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-022 | 27/10/2024 | Worthing UK | P. Davis | 26.5 | 154.8 | EXCEEDANCE | Compliant | Yes
INS-2024-023 | 26/11/2024 | Ware UK | S. Clark | 12.5 | 181.8 | Compliant | Compliant | No
INS-2024-024 | 10/12/2024 | Ware UK | P. Davis | 8.9 | 120.5 | Compliant | Compliant | Yes
INS-2024-025 | 16/01/2024 | Montrose UK | J. Adams | 23.3 | 219.1 | Compliant | EXCEEDANCE | Yes
INS-2024-026 | 18/02/2024 | Barnard Castle UK | J. Adams | 23.5 | 128.2 | Compliant | Compliant | Yes
INS-2024-027 | 07/03/2024 | Worthing UK | J. Adams | 28.5 | 159.4 | EXCEEDANCE | Compliant | Yes
INS-2024-028 | 08/04/2024 | Barnard Castle UK | J. Adams | 27.9 | 197.7 | EXCEEDANCE | Compliant | Yes
INS-2024-029 | 27/05/2024 | Stevenage UK | P. Davis | 20.1 | 142.7 | Compliant | Compliant | Yes
INS-2024-030 | 26/06/2024 | Ware UK | M. Brown | 31.4 | 101.1 | EXCEEDANCE | Compliant | Yes
INS-2024-031 | 12/07/2024 | Montrose UK | P. Davis | 29.9 | 185.8 | EXCEEDANCE | Compliant | Yes
INS-2024-032 | 07/08/2024 | Ware UK | J. Adams | 12.5 | 105.1 | Compliant | Compliant | Yes
INS-2024-033 | 20/09/2024 | Montrose UK | M. Brown | 23.4 | 175.8 | Compliant | Compliant | Yes
INS-2024-034 | 10/10/2024 | Montrose UK | S. Clark | 16.7 | 206.7 | Compliant | EXCEEDANCE | Yes
INS-2024-035 | 22/11/2024 | Stevenage UK | M. Brown | 33.7 | 172.6 | EXCEEDANCE | Compliant | Yes
INS-2024-036 | 02/12/2024 | Barnard Castle UK | M. Brown | 34 | 221.4 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-037 | 05/01/2024 | Barnard Castle UK | M. Brown | 26.9 | 103.9 | EXCEEDANCE | Compliant | Yes
INS-2024-038 | 16/02/2024 | Ware UK | S. Clark | 28.6 | 201.7 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-039 | 03/03/2024 | Stevenage UK | P. Davis | 25 | 147.5 | Compliant | Compliant | Yes
INS-2024-040 | 12/04/2024 | Worthing UK | P. Davis | 21.9 | 130.1 | Compliant | Compliant | Yes
INS-2024-041 | 25/05/2024 | Stevenage UK | P. Davis | 16.8 | 80.4 | Compliant | Compliant | Yes
INS-2024-042 | 28/06/2024 | Stevenage UK | P. Davis | 25.1 | 205.5 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-043 | 07/07/2024 | Worthing UK | S. Clark | 13.9 | 157.3 | Compliant | Compliant | Yes
INS-2024-044 | 18/08/2024 | Montrose UK | M. Brown | 16.7 | 131 | Compliant | Compliant | Yes
INS-2024-045 | 11/09/2024 | Stevenage UK | J. Adams | 23.3 | 167.4 | Compliant | Compliant | Yes
INS-2024-046 | 15/10/2024 | Stevenage UK | J. Adams | 10.7 | 221.1 | Compliant | EXCEEDANCE | Yes
INS-2024-047 | 15/11/2024 | Stevenage UK | P. Davis | 33.1 | 108.4 | EXCEEDANCE | Compliant | Yes
INS-2024-048 | 05/12/2024 | Barnard Castle UK | M. Brown | 13.5 | 203.9 | Compliant | EXCEEDANCE | Yes
INS-2024-049 | 03/01/2024 | Barnard Castle UK | S. Clark | 31.6 | 237.8 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-050 | 21/02/2024 | Ware UK | J. Adams | 10.2 | 199.6 | Compliant | Compliant | Yes
INS-2024-051 | 23/03/2024 | Ware UK | P. Davis | 18.7 | 135 | Compliant | Compliant | Yes
INS-2024-052 | 01/04/2024 | Ware UK | P. Davis | 25.7 | 206.7 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-053 | 17/05/2024 | Worthing UK | J. Adams | 10.1 | 186.9 | Compliant | Compliant | Yes
INS-2024-054 | 04/06/2024 | Worthing UK | M. Brown | 8.2 | 141.8 | Compliant | Compliant | Yes
INS-2024-055 | 03/07/2024 | Stevenage UK | J. Adams | 20.9 | 121.2 | Compliant | Compliant | Yes
INS-2024-056 | 05/08/2024 | Worthing UK | M. Brown | 16.5 | 238.6 | Compliant | EXCEEDANCE | Yes
INS-2024-057 | 03/09/2024 | Montrose UK | J. Adams | 25.3 | 201.9 | EXCEEDANCE | EXCEEDANCE | Yes
INS-2024-058 | 12/10/2024 | Ware UK | M. Brown | 24.5 | 109.5 | Compliant | Compliant | Yes
INS-2024-059 | 15/11/2024 | Ware UK | J. Adams | 32.8 | 190.9 | EXCEEDANCE | Compliant | Yes
INS-2024-060 | 04/12/2024 | Montrose UK | P. Davis | 32.2 | 105.2 | EXCEEDANCE | Compliant | Yes
Dashboard Evidence (Embedded Screenshots)

## Sampling
Sampling
Population | 60
Exceedances | 32
Selected Sample
Sample_No | Inspection_ID | Site | PM2.5_ugm3 | NOx_mgm3 | Evidence_Attached
1 | INS-2024-023 | Ware UK | 12.5 | 181.8 | No
2 | INS-2024-028 | Barnard Castle UK | 27.9 | 197.7 | Yes
3 | INS-2024-021 | Worthing UK | 30 | 253.5 | Yes
4 | INS-2024-051 | Ware UK | 18.7 | 135 | Yes
5 | INS-2024-009 | Ware UK | 20.1 | 157.3 | Yes

## Testing Table
Testing Attributes
Ref | Attribute | Procedure | Answer
A | Inspection schedule obtained and complete
B | Each inspection has photographic/screenshot evidence attached
C | Exceedances of emission thresholds flagged and escalated
D | Corrective actions documented and tracked to closure

## Corrective Actions
Corrective Action Tracker
CA_ID | Inspection_ID | Site | Issue | Action | Due_Date | Status | Escalated
CA-2024-001 | INS-2024-001 | Stevenage UK | NOx exceedance | Filter replacement | 15/02/2024 | Closed | Yes
CA-2024-002 | INS-2024-005 | Ware UK | PM2.5 exceedance | Stack recalibration | 15/06/2024 | Closed | No
CA-2024-003 | INS-2024-007 | Ware UK | PM2.5 exceedance | Filter replacement | 15/08/2024 | Closed | Yes
CA-2024-004 | INS-2024-008 | Montrose UK | PM2.5 exceedance | Stack recalibration | 15/09/2024 | Open - OVERDUE | Yes
CA-2024-005 | INS-2024-010 | Stevenage UK | NOx exceedance | Filter replacement | 15/11/2024 | Closed | Yes
CA-2024-006 | INS-2024-011 | Barnard Castle UK | PM2.5 exceedance | Stack recalibration | 15/12/2024 | Closed | Yes
CA-2024-007 | INS-2024-015 | Barnard Castle UK | PM2.5 exceedance | Filter replacement | 15/04/2024 | Closed | Yes
CA-2024-008 | INS-2024-016 | Worthing UK | NOx exceedance | Stack recalibration | 15/05/2024 | Closed | Yes
CA-2024-009 | INS-2024-018 | Ware UK | PM2.5 exceedance | Filter replacement | 15/07/2024 | Closed | Yes
CA-2024-010 | INS-2024-020 | Ware UK | PM2.5 exceedance | Stack recalibration | 15/09/2024 | Closed | Yes
CA-2024-011 | INS-2024-021 | Worthing UK | PM2.5 exceedance | Filter replacement | 15/10/2024 | Closed | Yes
CA-2024-012 | INS-2024-022 | Worthing UK | PM2.5 exceedance | Stack recalibration | 15/11/2024 | Closed | Yes
CA-2024-013 | INS-2024-025 | Montrose UK | NOx exceedance | Filter replacement | 15/02/2024 | Closed | Yes
CA-2024-014 | INS-2024-027 | Worthing UK | PM2.5 exceedance | Stack recalibration | 15/04/2024 | Closed | Yes
CA-2024-015 | INS-2024-028 | Barnard Castle UK | PM2.5 exceedance | Filter replacement | 15/05/2024 | Closed | Yes
CA-2024-016 | INS-2024-030 | Ware UK | PM2.5 exceedance | Stack recalibration | 15/07/2024 | Closed | Yes
CA-2024-017 | INS-2024-031 | Montrose UK | PM2.5 exceedance | Filter replacement | 15/08/2024 | Closed | Yes
CA-2024-018 | INS-2024-034 | Montrose UK | NOx exceedance | Stack recalibration | 15/11/2024 | Closed | Yes
CA-2024-019 | INS-2024-035 | Stevenage UK | PM2.5 exceedance | Filter replacement | 15/12/2024 | Closed | Yes
CA-2024-020 | INS-2024-036 | Barnard Castle UK | PM2.5 exceedance | Stack recalibration | 15/12/2024 | Closed | Yes
CA-2024-021 | INS-2024-037 | Barnard Castle UK | PM2.5 exceedance | Filter replacement | 15/02/2024 | Closed | Yes
CA-2024-022 | INS-2024-038 | Ware UK | PM2.5 exceedance | Stack recalibration | 15/03/2024 | Closed | Yes
CA-2024-023 | INS-2024-042 | Stevenage UK | PM2.5 exceedance | Filter replacement | 15/07/2024 | Closed | Yes
CA-2024-024 | INS-2024-046 | Stevenage UK | NOx exceedance | Stack recalibration | 15/11/2024 | Closed | Yes
CA-2024-025 | INS-2024-047 | Stevenage UK | PM2.5 exceedance | Filter replacement | 15/12/2024 | Closed | Yes
CA-2024-026 | INS-2024-048 | Barnard Castle UK | NOx exceedance | Stack recalibration | 15/12/2024 | Closed | Yes
CA-2024-027 | INS-2024-049 | Barnard Castle UK | PM2.5 exceedance | Filter replacement | 15/02/2024 | Closed | Yes
CA-2024-028 | INS-2024-052 | Ware UK | PM2.5 exceedance | Stack recalibration | 15/05/2024 | Closed | Yes
CA-2024-029 | INS-2024-056 | Worthing UK | NOx exceedance | Filter replacement | 15/09/2024 | Closed | Yes
CA-2024-030 | INS-2024-057 | Montrose UK | PM2.5 exceedance | Stack recalibration | 15/10/2024 | Closed | Yes
CA-2024-031 | INS-2024-059 | Ware UK | PM2.5 exceedance | Filter replacement | 15/12/2024 | Closed | Yes
CA-2024-032 | INS-2024-060 | Montrose UK | PM2.5 exceedance | Stack recalibration | 15/12/2024 | Closed | Yes

## Issue template
Issue / Exception Report
Issue_ID | Testing_Attribute | Severity | Description | Affected_Samples | Root_Cause | Remediation | Owner | Due_Date | Status